CASE STUDY: The Invasion | X-Suit Carnival (TVC)

Role: Line Producer

Project Size: Heavy visual effects commercial shot on a fixed £85,714 budget

2 days

£42,857 spent per day

250 crew members

( 🖼️ IMAGE PLACEHOLDER: Insert High-Resolution BTS Still or Textless Campaign Frame here )

Key Achievements:

- Money Saved: Avoided extra post-production costs by setting up the green screens correctly on set. We also made sure the high-wire stunts were completely safe to avoid any medical or legal costs.

- Project Status: Finished on time with all vendor bills paid in full.

- Software Used: Movie Magic Budgeting, QTAKE (for video playback), Scenechronize.

Project Overview:

Managing this visual-effects-heavy gaming ad required careful planning. Using my 21+ years of production experience, my job was to stick to the £85,714 budget, quickly hire a local crew of 250 people, and make sure the visiting agency clients had a comfortable space to watch the shoot.

Challenges & How We Solved Them

- 1. Fragile Costumes: * The Problem: The "X-Suit" costumes were heavy and broke easily during action scenes. If they broke, shooting would stop.

  - The Solution: I kept a repair team right on the studio floor with extra costume parts and tools. They fixed any damage instantly, so we never lost camera time.

- 2. Green Screen Lighting Issues: * The Problem: Shooting carnival scenes against massive green screens can cause green light to bounce onto the actors. This makes editing very expensive later.

  - The Solution: I booked a much larger studio so we could keep a big distance between the actors and the green screens. This gave the editors clean footage to work with.

- 3. Stunt Safety: * The Problem: Actors doing high-wire flying stunts faced real danger if the ropes or timing failed.

  - The Solution: I hired a special stunt rigging team and booked a full day just for slow, padded safety practice before the actual shoot. We finished with zero injuries.

- 4. Recording Gaming Screens: * The Problem: Filming mobile phone screens while moving cinema cameras usually causes the screens to flicker on video.

  - The Solution: I brought in a playback expert who matched the frame rates of the phones with our main cameras. This gave us perfect, flicker-free shots of the game.

- 5. Electrical Dangers: * The Problem: The set was a glowing carnival with a lot of high-voltage lights placed very close to the actors.

  - The Solution: I ordered strict electrical safety checks and kept the power lines for the set completely separate from the main camera lights. This removed any risk of electric shocks.

- 6. Managing a Large Crew: * The Problem: Feeding and moving 250 crew members during a tight two-day shoot can cause huge delays between shots.

  - The Solution: I divided the basecamp into different zones and staggered the lunch breaks. This kept the cameras rolling while the large crew ate in shifts.