CASE STUDY: Emami Fair and Handsome (TVC)

Role: Line Producer Project Size: Big celebrity ad campaign shot on a fixed £380,952 budget | 3 days | £126,984 spent per day | 175 crew members

( 🖼️ IMAGE PLACEHOLDER: Insert High-Resolution BTS Still or Textless Campaign Frame here )

Key Achievements:

- Money Saved: Stopped the shoot from running late during the star's strict 8-hour window by setting up lights on two sets at once.

- Set Security: Kept the set 100% private with no leaked photos of the superstar to the press.

- Software Used: Movie Magic Budgeting, Aspera (for sending files), SetKeeper.

Project Overview:

Running the physical shoot for this celebrity ad needed to be perfect. With over two decades of experience, I managed the £380,952 budget, handled a highly trained local crew, and kept the global agency clients happy. We met every single financial target we promised in the beginning.

Challenges & How We Solved Them

- 1. Safe Set Building:

  - The Problem: We had to build a huge, multi-level palace set in just 10 days. Rushing this could lead to a weak structure and put the crew in danger.

  - The Solution: I brought in a professional engineering company to check the scaffolding. I also hired more art department workers and split them into three 24-hour shifts to finish safely and on time.

- 2. Keeping the Celebrity Private:

  - The Problem: Having a huge superstar in a busy Mumbai studio always brings crowds and paparazzi, which could leak the new ad before it airs.

  - The Solution: I locked down the set completely. We set up rings of private security and used fingerprint scanners so only the working crew could get inside.

- 3. Heavy Power Needs:

  - The Problem: The massive set needed so many lights that it would have overloaded and tripped the studio's main power supply.

  - The Solution: I rented separate lighting trusses and two quiet generators to power our big lights from the outside. This completely bypassed the studio's own power limits.

- 4. Matching Real Sets with CGI:

  - The Problem: The physical set had to match perfectly with the fake digital backgrounds added later. Any mistake in measurements would cost a lot of money to fix in editing.

  - The Solution: I kept a visual effects expert on set and used special monitors. This let the director see how the digital background would look in real-time before filming every shot.

- 5. Short Time with the Star:

  - The Problem: The main celebrity was only booked for a strict 8-hour window. We had no time to stop and adjust lights.

  - The Solution: I ran two camera teams at the same time and lit a second set area in advance. When the star finished one shot, he walked right into the next one without waiting.

- 6. Avoiding Extra Union Pay:

  - The Problem: Working fast around the star's short schedule meant the setup and cleanup crews might have to work very long hours, which leads to heavy union overtime fines.

  - The Solution: I brought the lighting and grip teams in at different times. This kept the set working for 16 hours, but no single worker crossed their legal time limit.