CASE STUDY: Lava Mobiles (TVC)

Role: Line Producer Project Size: Fast-paced city commercial shot on a fixed £36,364 budget | 1 day | 100 crew members

( 🖼️ IMAGE PLACEHOLDER: Insert High-Resolution BTS Still or Textless Campaign Frame here )

Key Achievements

- Money Saved: Stopped the police from shutting down the shoot by getting all government permits approved early.

- Project Status: Finished 100% on time during a very tight 24-hour schedule.

- Software Used: Movie Magic Budgeting, Albert Carbon Calculator, SetKeeper.

Project Overview Shooting a big city commercial in just 24 hours leaves no room for mistakes. Using my 21+ years of production experience, I put together a fast crew of 100 people and locked down the budget instantly. My main goal was to handle all local problems so the visiting agency could focus purely on making a great video, while I kept the money safe and the shoot moving.

Challenges & How We Solved Them

- 1. Government & Traffic Rules: * The Problem: Filming action shots in South Mumbai’s historic areas carried a big risk. The local council or traffic police could easily stop the shoot, which would waste the agency's only filming day.

  - The Solution: I got full, written permissions from the city and the traffic police a week early. I hired off-duty police officers to stand around our set and keep us totally separate from the public and local officials.

- 2. Union Working Hours: * The Problem: Working a huge crew on such a fast schedule meant we would probably cross the strict 12-hour union work limit. That would trigger huge double-pay fines.

  - The Solution: I gave the lighting and technical teams different starting times. Because their shifts overlapped, the set kept working all day without any single person going into overtime.

- 3. Keeping the Phone a Secret: * The Problem: Filming a brand-new, unreleased smartphone on the busy streets of Mumbai meant someone could easily take a picture and leak it online.

  - The Solution: I put up a strict three-layer security circle using private guards and tall black curtains to completely block the public's view.

- 4. Keeping Clients Comfortable: * The Problem: Asking the visiting agency clients to stand in the middle of a noisy Mumbai street would make them tired and slow down their creative decisions.

  - The Solution: I rented a clean, air-conditioned room away from the street. I ran private video cables to screens in that room, so they could watch the shoot comfortably and keep the new phone a secret.

- 5. Racing Against the Sun: * The Problem: Because we needed natural sunlight, any delay meant we would lose the sun and ruin the final shots of our 24-hour schedule.

  - The Solution: I planned every single shot using a sun-tracking app. We moved the crew exactly in time with the sun's path to use every single minute of good daylight.

- 6. Paying Vendors on the Spot: * The Problem: Spending a large amount of money in just 24 hours meant that if we paid the heavy equipment suppliers late, they might take their gear back and stop the shoot.

  - The Solution: I used a fast online payment system on set. The production accountant paid all the machinery bills the moment the equipment arrived, making sure we had zero delays.