CASE STUDY: Meril (TVC)

Role: Line Producer Project Size: Studio sports shoot with a celebrity, shot on a fixed £71,428 budget | 2 days | £35,714 spent per day | 150 crew members

( 🖼️ IMAGE PLACEHOLDER: Insert High-Resolution BTS Still or Textless Campaign Frame here )

Key Achievements

- Money Saved: Prevented huge damage bills by hanging a safety net under the studio lights. Got the most out of the celebrity's time by using a stand-in for lighting tests.

- Project Status: Finished 100% on schedule and strictly followed the agreed budget rules.

- Software Used: Movie Magic Budgeting, QTAKE (for robot camera control), Frame.io.

Project Overview Taking charge of this sports ad meant managing a huge indoor set build and a famous sports star. Bringing 21+ years of experience to the table, I handled the £71,428 budget, managed a large local crew, and kept the visiting agency safe. I stopped the project from going over budget and respected all the original cost plans perfectly.

Challenges & How We Solved Them

- 1. Making the Fake Stadium Look Real: * The Problem: Building a fake cricket pitch and stadium seats inside a plain studio could look very cheap and fake on a high-quality camera.

  - The Solution: I bought real sports grass and built a proper seating area. We also used a lot of smoke machines to make the background look deep, just like a real stadium on TV.

- 2. Safe Robot Cameras: * The Problem: Trying to film a fast cricket swing indoors required very fast, robotic cameras. These machines move so quickly they could easily hit and hurt the actors.

  - The Solution: I programmed the exact path for the robot cameras a day early. We set hard safety lines on the floor before the celebrity even walked into the room.

- 3. Looking After Kids and Seniors: * The Problem: Having very active kids and older grandparents on a noisy set at the same time could make everyone very tired and cause health worries.

  - The Solution: I built separate, cool resting rooms for the children and the seniors. We only brought them out to film in short, careful blocks of time so they wouldn't get exhausted.

- 4. Celebrity Time Limits: * The Problem: The sports star’s contract only gave us a very short time with him on set. We had zero time to test the lights once he arrived.

  - The Solution: I hired a stand-in who had the exact same height and body shape as the star. We used him to set up all the lights perfectly. When the real star walked in, we were ready to shoot instantly.

- 5. Protecting the Studio Roof: * The Problem: Hitting a real cricket ball hard indoors meant it would probably hit and break the studio's very expensive ceiling lights. That would hurt people and cost us a lot in fines.

  - The Solution: I hung a strong, clear safety net right underneath the lighting grid. It safely caught any flying balls without blocking the light.

- 6. Handling Huge Video Files: * The Problem: Filming slow-motion sports shots creates huge video files. If we took too long to copy those files, the cameras would have to stop and wait.

  - The Solution: I placed a very fast computer server right next to the camera team. This allowed us to copy and check the footage instantly, so the cameras never had to stop rolling.