CASE STUDY: Hyundai (Global TVC)

Role: Line Producer Project Size: A fast two-day car commercial shot in Georgia on a fixed £240,000 budget | £120,000 spent per day

( 🖼️ IMAGE PLACEHOLDER: Insert High-Resolution BTS Still or Textless Campaign Frame here )

Key Achievements

- Money Saved: Avoided huge waiting fees by getting the cars through customs early. Saved on extra staff hours by buying car parts instantly on set.

- Set Security: Kept the new, unreleased car completely hidden from the public with zero leaks.

- Software Used: Movie Magic Budgeting, Aspera (for sending big files), QTAKE (for video playback).

Project Overview I took full charge of this international car commercial, working with a very tight 48-hour deadline. Using my 21+ years of production experience, my job was to protect the budget, create a very safe stunt driving area, and make sure we followed the approved costs without hurting the director's creative ideas.

Challenges & How We Solved Them

- 1. Bringing in Stunt Cars:

  - The Problem: Customs delays at the Georgian border could trap our tracking vehicles and ruin our short schedule.

  - The Solution: I hired a car import expert a month early. We cleared all the paperwork ahead of time so the heavy stunt cars were parked at the set a full day before filming started.

- 2. Keeping the Car Secret:

  - The Problem: People walking by could take photos of the new Hyundai and post them online, which would ruin the global launch.

  - The Solution: I booked a private test track for the main driving shots. We used custom blackout tents to hide the car when the cameras were off, and I took away all crew phones before they walked onto the track.

- 3. Huge Video Files:

  - The Problem: Trying to send massive, high-quality video files to the editors using slow hotel internet would mean missing our daily deadlines.

  - The Solution: I brought in a data expert with a fast, portable computer server. We backed up all the heavy video files right there on set and shipped physical hard drives on overnight flights to the editors.

- 4. Client Safety:

  - The Problem: If the brand team tried to follow the cars closely, they could get hurt and distract the stunt drivers.

  - The Solution: I rented a nice double-decker bus and turned it into a mobile viewing room. I put live wireless video screens inside so the clients could watch the fast driving safely from far away.

- 5. Language Barriers:

  - The Problem: The foreign director and the local Georgian stunt drivers did not speak the same language. This could lead to mixed-up directions and dangerous high-speed crashes.

  - The Solution: I put a professional car translator right in the lead tracking vehicle. This made sure every radio command was translated instantly, keeping the chase scenes completely safe and on time.

- 6. Fast Purchases on Set:

  - The Problem: Popped tires or broken car parts from hard drifting would stop the shoot right away if we had to wait for normal office approvals to buy replacements.

  - The Solution: I gave our local buyer a special cash card just for auto parts. This skipped the usual paperwork, letting the team buy new tires on the spot and keep the cameras rolling.