CASE STUDY: Kit Kat - Global TVC

Role: Line Producer Project Size: A quick three-day international commercial shot in Lviv, Ukraine on a set £190,000 budget | Over £63,000 spent per day

( 🖼️ IMAGE PLACEHOLDER: Insert High-Resolution BTS Still or Textless Campaign Frame here )

Key Achievements

- Money Saved: Stopped huge extra pay fines by putting the makeup tents right next to the stage. Avoided delays by paying local suppliers immediately.

- Project Status: Finished 100% on time and exactly within the agreed budget limits.

- Software Used: Movie Magic Budgeting, SetKeeper, Teradek (for wireless video).

Project Overview I ran the physical filming for this fast-moving commercial under a strict three-day limit. Relying on my 21+ years of experience, my goal was to manage the £190,000 budget, handle the famous actors, and host the agency clients on set while sticking closely to the original financial plan.

Challenges & How We Solved Them

- 1. Moving Gear Across Borders:

  - The Problem: Taking heavy, special camera gear through different countries meant customs could hold our equipment and waste our entire first shoot day.

  - The Solution: I hired a special shipping agent a month before the shoot. I got all the packing lists cleared early, making sure the trucks reached the studio a full 24 hours before the first lighting setup.

- 2. Managing Famous Actors:

  - The Problem: Handling two lead actors who had strict, overlapping working hours was risky. Any walking time between their resting rooms and the set could push them into expensive overtime.

  - The Solution: I created a zero-walking daily plan. I built two separate hair, makeup, and clothing rooms right next to the active camera area, keeping both stars strictly within their allowed 12-hour windows.

- 3. Hosting the Clients:

  - The Problem: Having a large group of agency and Nestle clients standing on the studio floor would crowd the crew and make too much noise during filming.

  - The Solution: I built a separate, soundproof viewing room away from the main action. I ran private TV screens and a direct microphone in there, so the clients felt involved while the crew had plenty of quiet space to work.

- 4. Keeping the Product Secret:

  - The Problem: Letting local studio workers see the newly designed Kit Kat wrapper before it was officially released was a huge risk for social media leaks.

  - The Solution: I made sure the set was totally closed off to outsiders. I took away everyone's mobile phones at the door and covered all the studio windows with black cloth to keep the brand's new look completely private.

- 5. Talking to Local Crews:

  - The Problem: The English-speaking agency and the local Ukrainian lighting team could not understand each other. This could cause big delays and waste expensive daylight hours.

  - The Solution: I placed bilingual floor managers in every single key department. This meant the director's requests were translated the very second he spoke, keeping the shoot moving as fast as possible without any mix-ups.

- 6. Paying Local Workers Quickly:

  - The Problem: If we were slow to pay the local daily workers and gear suppliers, they might walk out and stop the shoot the next day.

  - The Solution: I set up a fast digital payment system handled by a dedicated accountant on set. We paid all the bills the exact minute we finished shooting each night, which earned the local crew's trust for the next morning.