CASE STUDY: Gangster Ganga (Hindi Short Film)

Role: Executive Producer Project Size: £45,000 budget | 4-day shoot | £11,250 spent per day

( 🖼️ IMAGE PLACEHOLDER: Insert Textless Key Art or High-Resolution BTS Still here )

Key Achievements

- Money Saved: Kept the full emergency fund of £5,700 totally safe and saved £1,200 on renting equipment.

- Project Status: Finished 100% on time without owing any extra union overtime pay.

- Software Used: Movie Magic Budgeting, SetKeeper (for daily schedules).

Project Overview I made a very clear and tight plan to shoot this short film within strict time and money limits. Using my 21+ years of production experience, my goal was to make the film look great on screen, keep the emergency money untouched, and follow all union rules perfectly while filming in crowded Mumbai areas.

Challenges & How We Solved Them

- 1. Moving in Heavy Traffic:

  - The Problem: Moving the whole film crew across Mumbai in the middle of the day could waste 15% of our time in traffic, which would lead to huge overtime fines.

  - The Solution: I sent the lighting trucks two hours before the main crew finished their first shot. The second location was fully lit and ready exactly when the director got there, so we did not lose a single minute.

- 2. Following Union Rules:

  - The Problem: Making the crew work past their standard 12-hour shift to finish a lot of scenes could make the union angry and double our daily costs.

  - The Solution: I set a strict rule to stop filming on time. I added a required 45-minute packing time to the daily schedule. The crew was always packed and signed out before any late fines kicked in.

- 3. Shooting a Lot of Pages Fast:

  - The Problem: Trying to shoot 7.5 pages of the script every single day in real, working houses meant the camera team might get confused and miss important scenes.

  - The Solution: I asked the main actors and the head cameraman to practice on the weekend. Planning all the camera angles early meant the crew could shoot very fast on set without stopping to think.

- 4. Small Shooting Spaces:

  - The Problem: Using normal, heavy camera tracks inside tiny Mumbai apartments would cost an extra £1,200 and take too long to set up.

  - The Solution: I changed the plan and rented small, easy-to-move camera parts instead. This took up much less space, cut our rental bill by 35%, and let the crew get ready for the next shot in under 15 minutes.

- 5. Sudden Rain and Bad Weather:

  - The Problem: Unpredictable rain right before the monsoon could easily stop us from shooting outside, which would ruin our tight four-day plan.

  - The Solution: I picked indoor backup locations that were less than 100 meters away from our outdoor spots. When the rain started, I simply moved everyone inside right away, so we did not lose a single hour of work.

- 6. Keeping Video Files Safe:

  - The Problem: Moving around quickly for four days meant someone could easily drop or lose a hard drive, which would ruin the video files.

  - The Solution: I put a computer expert right on the set. They made sure every single video clip was copied and checked safely before the camera truck ever drove away.