CASE STUDY: Ittaa Kittaa (Gujarati Feature Film)

Role: Head of Production Project Size: £285,000 budget | 150 crew members | Shot in rural Gujarat villages

( 🖼️ IMAGE PLACEHOLDER: Insert Textless Key Art or High-Resolution BTS Still here )

Key Achievements

- Money Saved: Stopped local village shops from overcharging us by locking in fixed prices early.

- Going Green: Produced zero diesel smoke during the day by plugging directly into the local power grid.

- Software Used: Movie Magic Budgeting, Scenechronize (for planning), Albert Carbon Calculator.

Project Overview This movie required us to find and control large real-life locations in distant parts of Gujarat. As the main person in charge, I used my 21+ years of production experience to run the shoot smoothly and meet the strict rules of big Indian investors. I personally watched over every team, making sure the crew stayed safe in the harsh weather while keeping a very tight grip on the money.

Challenges & How We Solved Them

- 1. Bringing Gear to Remote Villages:

  - The Problem: Filming in small villages that have zero film equipment meant if one camera part broke, the whole shoot would stop completely.

  - The Solution: I brought a fully complete setup all the way from Mumbai. I signed fixed-price deals early for 30 cars, multiple cameras, big trucks, and food. This stopped local people from suddenly asking for more money.

- 2. Shooting in Extreme Heat (44°C):

  - The Problem: Filming long talking scenes outside in the 44-degree summer sun could easily make the crew pass out or need an ambulance.

  - The Solution: I changed the work hours so we only shot early in the morning and late at night. I also set up huge cooling fans at the resting camp. We finished the whole shoot with zero people falling sick from the heat.

- 3. Saving Fuel and Reducing Smoke:

  - The Problem: Using normal diesel generators to power lights for 150 people in extreme heat burns a lot of fuel, costs a lot of money, and creates heavy black smoke.

  - The Solution: I talked to the Gujarat State Electricity Board and got a direct power line for our main locations. We did not have to turn on the diesel generators during the day at all, which saved a huge amount of fuel money and kept the air clean.

- 4. Getting Government Permissions:

  - The Problem: Filming inside old, government-owned buildings could lead to officials locking the doors or asking for bribes if the paperwork was wrong.

  - The Solution: I sent a small team to the town three months early to finish all the city paperwork. We signed clear rental papers directly with the state leaders, which protected our budget from sudden extra fees.

- 5. Managing Local and City Workers Together:

  - The Problem: Mixing highly trained Mumbai union workers with hundreds of local village background actors could create confusion with daily pay and start arguments.

  - The Solution: I used a simple online payment system. I gave the local village workers very clear daily contracts that matched the safe rules used by the Mumbai union. This kept everyone happy and protected our cash.

- 6. Tracking the Daily Cash:

  - The Problem: Moving a huge group of 150 people to different villages every few days usually leads to lost cash and missing bills for food and travel.

  - The Solution: I stopped using cash for daily needs. I made sure every driver, food supplier, and camp owner signed a contract and got paid directly through bank transfers. This gave the investors perfectly clean financial reports at the end.