CASE STUDY: Bridge

Role: Executive Producer (United Kingdom) Project Size: £3.5 Million budget | 30-day shoot | £116,666 spent per day

( 🖼️ IMAGE PLACEHOLDER: Insert Poster or High-Resolution BTS Still here )

Key Achievements

- Money Saved: Kept over £320,000 perfectly safe by avoiding huge upfront deposits, late-night crew fines, and expensive city permits.

- Tax Cash Back: Got 39.75% of our British spending returned as pure cash using the UK Independent Film Tax Credit.

- Software Used: Movie Magic Budgeting, Sargent-Disc (for paying the crew), SetKeeper (for safe script sharing).

Project Overview As the Executive Producer for Prism Motion Pictures, I ran the entire physical shoot and handled all the money in the UK. Using my 21+ years of experience, my main goal was to protect the investors' cash, hire a fast and smart local crew, and finish the movie exactly on the promised date.

Challenges & How We Solved Them

- 1. Paying for Gear (Cash Flow):

  - The Problem: Paying for everything upfront on a £3.5 million movie drains your bank account too fast, putting the whole project in a dangerous cash crunch.

  - The Solution: I sat down with our main equipment and transport shops and agreed to pay them 30 days later. This kept our daily cash totally healthy and stopped £200,000 from leaving our account in the very first week.

- 2. Shooting in Busy London:

  - The Problem: Filming in the middle of central London usually means paying massive city fees and dealing with angry locals, which can easily force the police to shut you down.

  - The Solution: I changed our plan so we only shot during quiet weekend hours with a much smaller camera team. We did not have to block any major roads, which saved us £45,000 in city permit fees.

- 3. UK Labor Rules (BECTU):

  - The Problem: Asking a British crew to work the long hours we usually do in India would break their local labor rules. We would get hit with massive overtime fines and the union might walk out.

  - The Solution: I brought different departments in at different times of the day. The set stayed open and busy for 14 hours, but no single person worked past their normal 10-hour shift. This simple trick saved us about £60,000 in extra pay.

- 4. Keeping the Story a Secret:

  - The Problem: With hundreds of local daily workers walking around, someone could easily take pictures and leak the movie's plot to the press before it was finished.

  - The Solution: I made every single worker sign strict privacy rules. I only gave out secure, watermarked digital script pages for that exact day's work. We finished the movie with zero leaks to the public.

- 5. Closing the Office Fast:

  - The Problem: Keeping the UK accountants working for weeks after the shoot is over costs a lot of extra money.

  - The Solution: I made a hard rule that all department heads had to hand in their final bills immediately. We closed the UK office just five days after the cameras stopped, saving £15,000 in leftover accounting fees.

- 6. Claiming the UK Tax Refund:

  - The Problem: If you don't follow the exact rules for the UK tax refund, you lose a massive chunk of your budget forever.

  - The Solution: I kept our UK bills totally separate from our international bills from day one. Because our paperwork was so clean, we easily claimed the new UK Independent Film Tax Credit, bringing 39.75% of our British spending right back as cash.