CASE STUDY: Dunki

Role: Line Producer (Mumbai & Budapest) Project Size: £8.5 Million budget | 75-day shoot | £113,333 spent per day

( 🖼️ IMAGE PLACEHOLDER: Insert Poster or High-Resolution BTS Still here )

Key Achievements

- Money Saved: Kept over £2 Million safe by stopping border delays, dodging high bank fees, and building sets locally instead of flying them.

- Tax Cash Back: Easily passed the government check to get a 30% cash refund from the Hungarian Film Tax Rebate.

- Software Used: Movie Magic Budgeting, Scenechronize (for tracking gear), Albert Carbon Calculator.

Project Overview I managed the global shoot for Red Chillies Entertainment, focusing heavily on moving the crew between the UK and Budapest. With over two decades of production experience, my absolute priority was to keep a massive crew moving smoothly across borders without losing a single day on the calendar.

Challenges & How We Solved Them

- 1. Crossing Borders with Heavy Gear:

  - The Problem: Moving big camera and lighting trucks from the UK to Hungary usually gets stuck at customs for three days. Sitting and waiting would cost us £113,000 every single day in crew pay.

  - The Solution: I hired a special shipping agent and prepared all the border papers (ATA Carnets) early. Our trucks crossed the border in just 12 hours, meaning we never lost a shoot day and saved around £340,000 in wasted time.

- 2. Hidden Bank Fees:

  - The Problem: We had to pay bills in British Pounds, Euros, and Hungarian Forints. Standard daily bank transfers change rates every day and charge hidden fees, which eats up the budget very fast.

  - The Solution: I sat down with our banks before the shoot started and locked in a flat, bulk exchange rate. By fixing the price early, we protected our money completely and saved £120,000 in conversion fees.

- 3. Getting Two Visas at Once:

  - The Problem: If we waited for the UK visas to clear before we applied for the Hungarian visas, our entire travel schedule would be pushed back by two full weeks.

  - The Solution: I ran both applications at the exact same time. This kept our travel plans moving perfectly and stopped us from losing a massive £1.5 million in delayed shooting costs.

- 4. Building Sets Locally:

  - The Problem: Flying huge, heavy set pieces on an airplane from the UK to Hungary costs a fortune and creates a lot of terrible air pollution.

  - The Solution: I hired a local team in Hungary to build the exact same sets right there on the ground. It cost us £30,000 to build, but we saved £85,000 on flight fees and kept our air pollution score very low.

- 5. Protecting the Lead Actor's Travel:

  - The Problem: If our main star's flight between countries got delayed or cancelled, the whole set would have to shut down, wasting a huge amount of money that day.

  - The Solution: I bought special travel insurance just for the main actors. When a few small delays actually happened, the insurance paid for the lost time, meaning the studio paid absolutely nothing out of pocket.

- 6. Perfect Hungarian Paperwork:

  - The Problem: Hungary gives a great cash refund, but only if every single receipt is perfect. Messy bills mean you fail the National Film Institute check and get nothing.

  - The Solution: I hired a local Hungarian accountant to watch every single penny spent on the ground. We passed the government audit easily and got the 30% cash refund sent straight back to the studio.