CASE STUDY: Ganapath

Role: Line Producer (United Kingdom) Project Size: £15 Million budget | 90-day shoot | £166,666 spent per day

( 🖼️ IMAGE PLACEHOLDER: Insert Poster or High-Resolution BTS Still here )

Key Achievements

- Money Saved: Saved over £1.9 Million by building our own studio, stopping injuries, clearing customs early, and using fast internet instead of mail.

- Tax Cash Back: Got 25.5% of our British spending returned as pure cash using the UK Audio-Visual Expenditure Credit.

- Software Used: Movie Magic Budgeting, Sargent-Disc, Albert Carbon Calculator, Frame.io (Camera to Cloud).

Project Overview For this massive action movie, I oversaw all operations in the UK. Big stunts and a £15 million budget require very strict safety rules and a tight grip on the money. Over my 21-year career, I have learned that the bigger the action scenes are, the more closely you need to watch the daily spending.

Challenges & How We Solved Them

- 1. Expensive Studio Rent:

  - The Problem: Normal film studios in London are incredibly expensive because they are always fully booked by big Hollywood movies. Renting one would have blown our budget in the first month.

  - The Solution: Instead of a normal studio, I found a huge, empty storage warehouse outside the city and turned it into our filming space. This one choice saved the movie £750,000 in rent over the three months.

- 2. Stopping Stunt Injuries:

  - The Problem: A bad injury during our big fight scenes would force the set to shut down, costing over £166,000 a day and causing huge insurance headaches.

  - The Solution: I brought in top British safety experts early on to test every flying wire and landing mat. Nobody got hurt during the entire 90-day shoot, which meant we saved our full £500,000 emergency fund.

- 3. Importing Custom Stunt Gear:

  - The Problem: We flew in custom-built stunt equipment from Mumbai. UK border guards always stop and check strange metal gear, which could have trapped our equipment for a week.

  - The Solution: I worked with UK customs to check all the gear through photos and paperwork before it even left India. It landed and went straight to the set, saving us nearly £660,000 in waiting time.

- 4. Using Clean Power:

  - The Problem: Using old diesel generators for huge night shoots creates dirty smoke. This breaks strict UK green rules and leads to heavy fines.

  - The Solution: I banned garbage from going to landfills and powered our lights with totally silent, giant battery packs. This kept the air clean, got us a top green award, and cut our fuel bills by £40,000.

- 5. Sending Video Files Safely:

  - The Problem: Putting heavy 4K video hard drives on airplanes to send back to editors in India is risky. If a drive gets lost or broken, the footage is gone, and mailing them costs thousands.

  - The Solution: I set up a super-fast private internet server right on the set. We uploaded the video files every night, saving £30,000 in mailing fees and letting the editors in Mumbai start working the very next morning.

- 6. Claiming the UK Tax Refund:

  - The Problem: When you mix foreign and local crew on a big movie, it is hard to prove to the UK government exactly how much money stayed in Britain for the tax refund.

  - The Solution: I set up a totally separate payroll system just for our British workers and local shops. This clean split let us easily claim the UK Audio-Visual tax credit, getting 25.5% of our British spending back as pure cash.