CASE STUDY: A Broken Heart (Music Video)

Role: Executive Producer Project Size: A high-quality story music video filmed on a fixed £30,000 budget over 2 days, spending £15,000 a day with 10 crew members in Dubai.

( 🖼️ IMAGE PLACEHOLDER: Insert High-Resolution BTS Still or Textless Music Video Frame here. Strictly no marketing text. )

Key Achievements

- Money Saved: Saved our £3,500 deposit by carrying gear carefully so we didn't break the building's strict rules.

- Delivery Status: Finished exactly on time without the cameras breaking down in the extreme heat.

- Software Used: Movie Magic Budgeting, SetKeeper, QTAKE (for checking video).

Project Overview Relying on 21+ years of experience, I ran this music video by taking a fast, foreign crew right into Dubai. I guarded the tight £30,000 budget and took care of the visiting agency clients so they could focus only on the creative parts. We made the video look like a big movie while following all the spending rules and cutting out extra middleman fees.

Challenges & How We Solved Them

- 1. Getting Visas for the Actors:

  - The Problem: Dubai airport security flagged our four main actors entering the country at the same time. If they got stuck at the airport, we would waste £15,000 waiting for them.

  - The Solution: I called a trusted visa agency in the Middle East and got all the actors cleared together as a group. They walked right through customs and arrived on set with 12 hours to spare.

- 2. Filming in a Fancy Penthouse:

  - The Problem: The managers of the downtown building saw our big camera gear and almost kicked us out. If they did, we would lose our £3,500 deposit instantly.

  - The Solution: I quickly changed our plan. I split the crew into tiny groups and we brought the heavy gear up the elevator very slowly over three hours. This kept the building managers completely happy.

- 3. Recording Sound in the Desert:

  - The Problem: Loud, hot winds blowing through the desert sand dunes would ruin the actors' voices. Fixing this back in a London sound studio later would cost an extra £2,000.

  - The Solution: I bought special fuzzy microphone covers from a local shop and completely changed the daily schedule. We filmed all the talking scenes at the crack of dawn when the desert wind was completely still.

- 4. Protecting Cameras from the Sun:

  - The Problem: The extreme Middle Eastern sun was so hot it was pushing the digital cameras to the edge. If they got too hot, they would shut down completely.

  - The Solution: I made a very strict rule for the camera team. They had to cover the cameras with shiny foil blankets and tie frozen ice packs to them after every single take. The cameras never stopped working once.

- 5. Flying Drones in Dubai:

  - The Problem: Flying a camera drone in the Dubai desert without the right government papers can get you arrested and your expensive drone taken away.

  - The Solution: I spent weeks doing the right paperwork with the UAE aviation office. I hired a local, fully licensed drone pilot to fly the exact paths they approved, getting beautiful shots perfectly legally.

- 6. Putting Down Big Deposits:

  - The Problem: Camera rental shops in Dubai ask for huge amounts of security money upfront. Paying that would drain our entire £30,000 budget before we even started.

  - The Solution: I used my banking connections to give the rental shops a special bank letter (escrow) instead of cash. This promised they were safe but let me keep our actual cash to pay for the daily shoot.